## Sheet1
# | Bucket | Task | User | Program | Status | Date
1 | Data | Acquire raw data from Kaggle | CG | n/a | Complete | 2018-04-10
2 | Data | Add IMDB episode ratings to episode_info table | All | Excel | Complete | 2018-04-10
3 | Data | Clean / Parse the Characters column in the scripts table | CG | Python | Complete | 2018-04-12
4 | Data | Create variable: # of Characters | tbd | Python | On Hold |  | reload original CSV, and do a count of unique characters per episode
5 | Data | Create variable: # of Lines of Dialogue | tbd | Python |  |  | count # of rows per episode
6 | Data | Create variable: Avg Dialogue Sentiment | tbd | Python | In Progress | 2018-04-12 | VADER Sentiment
7 | Data | Create variable: Main Character Sentiment | tbd | Python |  |  | add a new column -- if MainChar then == Sentiment else NaN
8 | Data | Create 4 variables: Individual Main Char Sentiment | tbd | Python |  |  | same as above but specific to each MainChar
9 | Analysis | Regression Analysis to Predict IMDB Rating | tbd | Python / R
10 | Product | Create dashboard | CB | HTML
X | Data | get a reviews data set for sentiment analysis
Note on C9: Chris Gargano: Jerry Sentiment George Sentiment Kramer Sentimet Elaine Sentiment